## Dashboard
Weekly Dashboard
Program
Metrics | Value | Status
Program % Completion (Actual) | 43.2% | On Track
Program % Completion (Actual) | 46% | Info
Schedule Variance | -2.8% | On Track
Cost | Value | Status
Metrics | Value | Status
Contract Budget | 500000 | Info
Forecast Final Cost | 491000 | On Track
Forecast Variance | 9000 | On Track
Spent to Date | 16366.6667 | Info
RFI
Metrics | Value | Status
Open RFIs | 8 | At Risk
Overdue RFI | 3 | Critical
Safety & Program
Metrics | Value | Status
TRIFR
Open Safety Incidents
Days to PC